## Week1
PROJECT REPORT
Group | Group 1
Week | 9 May 2022 to 15 May 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Pick a topic | Complete | We chose "Online Women Fashion Shop" as our topic
2 | Requirement analysis | In Progress
3 | Writing backlog | In Progress
4 | Determine priorities for requirements | Complete
5 | Create a group and project on GitLab | Complete
6 | Writing the first part of SRS | In Progress
7 | GitLab training | Complete
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Requirement analysis | All members
2 | Filling in weekly report | All members
3 | Determine priorities for requirements | NguyenPT, DuyLVL
4 | Writing the first part of SRS | All members
5 | Writing backlog | All members
6 | Pick a topic | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Getting to know GitLab | Completed
2 | Sketching web's skeleton using Figma | Completed
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Writing SRS documents
2 | Weekly report
3 | Design database and ERD
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Determining project workflow on GitLab | KhanhTTV

## Week2
PROJECT REPORT
Group | Group 1
Week | 16 May 2022 to 22 May 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Discuss coding convention | Complete
2 | Design database and ERD | Complete
3 | Adding overview for SRS | Complete
4 | Write SRS functional requirements | In Progress
5 | Code sign up + login screen | Complete
6 | Code admin screen features | In Progress
7 | Adding database data | In Progress
8 | Write overview for SDD | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Discuss coding convention | All members
2 | Design database and ERD | All members
3 | Adding overview for SRS | All members
4 | Write SRS functional requirements | TrungTD, DuyLVL, NguyenPT
5 | Code sign up + login screen | ManHG
6 | Code admin screen features | KhanhTTV, ManHG
7 | Adding database data | All members
8 | Write overview for SDD | KhanhTTV, DuyLVL, TrungTD
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Requirements regrading admin features | Completed
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Writing SRS documents
2 | Weekly report
3 | Writing SDD documents
4 | Coding manager screen
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Week3
PROJECT REPORT
Group | Group 1
Week | 23 May 2022 to 29 May 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code product management screen | In Progress
2 | Code order management | In Progress
3 | Code Statistic Dashboard | In Progress
4 | Code Home Screen | In Progress
5 | Insert more data into database | Complete
6 | Edit database ERD | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code product management screen | TrungTD
2 | Code order management | DuyLVL
3 | Code Statistic Dashboard | NguyenPT
4 | Code Home Screen | ManHG, KhanhTTV
5 | Insert more data into database | All members
6 | Edit database ERD | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Homepage UI design | Complete
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Draw sequence diagram for basic features
2 | Draw class diagram for basic features
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week4
PROJECT REPORT
Group | Group 1
Week | 30 May 2022 to 5 June 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Manager Product screen | Completed
2 | Code Manager Product Detail screen | In Progress
3 | Code Add Product screen | In Progress
4 | Code pagination | Completed
5 | Code Dashboard screen | Completed
6 | Add upload image function | In Progress
7 | Coding Google Login feature | In Progress
8 | Integrate Tawk.to chat | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Manager Product screen | KhanhTTV
2 | Code Manager Product Detail screen | ManHG, KhanhTTV
3 | Code Add Product screen | KhanhTTV
4 | Code pagination | TrungTD
5 | Code Dashboard screen | NguyenPT
6 | Add upload image function | ManHG
7 | Coding Google Login feature | DuyLVL | Google + Facebook login
8 | Integrate Tawk.to chat | ManHG
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Employee Screen
2
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week5
PROJECT REPORT
Group | Group 1
Week | 6 June 2022 to 12 June 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Coding add product screen | Complete
2 | Coding forgot password feature | Complete
3 | Coding customer product detail screen | Complete
4 | Draw sequence diagrams | In Progress
5 | Coding home screen | Complete
6 | Adding and formatting product images | Complete
7
8
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Coding add product screen | ManHG
2 | Coding forgot password feature | TrungTD
3 | Coding customer product detail screen | KhanhTTV
4 | Draw sequence diagrams | TrungTD, DuyLVL
5 | Coding home screen | NguyenPT
6 | Adding and formatting product images | NguyenPT
7
8
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Code manager product details screen
2 | Code manage cart feature
3 | Code employee screen
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week6
PROJECT REPORT
Group | Group 1
Week | 13 June 2022 to 19 June 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Search Product screen | Complete
2 | Add employee pages | Complete
3 | Code Statistic Dashboard screen | In Progress
4 | Code Category Screen | Complete
5 | Code Manager Product Detail screen | In Progress
6 | Code Manage Cart Screen | Complete
7 | Add order status data | Complete
8 | Fix bug Home page | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Search Product screen | KhanhTTV
2 | Add employee pages | TrungTD
3 | Code Statistic Dashboard screen | NguyenPT
4 | Code Category Screen | KhanhTTV
5 | Code Manager Product Detail screen | ManHG
6 | Code Manage Cart Screen | DuyLVL
7 | Fix bug viewing products | NguyenPT
8
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Write SDD
2 | Code Checkout Screen
3 | Code Payment Method function
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week7
PROJECT REPORT
Group | Group 1
Week | 20 June 2022 to 26 June 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code Checkout screen | In Progress
2 | Code Payment method | Complete
3 | Code Statistic Dashboard | In Progress
4 | Code Product Management Detail | In Progress
5 | Code Order Management | In Progress
6 | Write SDD | In Progress
7
8
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Checkout screen | DuyLVL, TrungTD
2 | Code Payment method | KhanhTTV
3 | Code Statistic Dashboard | NguyenPT
4 | Code Product Management Detail | ManHG
5 | Code Order Management | DuyLVL
6 | Write SDD | TrungTD, KhanhTTV
7
8
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1
2
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week8
PROJECT REPORT
Group | Group 1
Week | 27 June 2022 to 3 July 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Modify Statistic Dashboard | Complete
2 | Code Confirmation Mail | In Progress
3 | Modify Order Management Screen | Complete
4 | Code Persistent cart | Complete
5 | Code Order History | In Progress
6 | Draw sequence diagram | In Progress
7
8
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Modify Statistic Dashboard | NguyenPT
2 | Code Confirmation Mail | TrungTD
3 | Modify Order Management Screen | DuyLVL
4 | Code Persistent cart | KhanhTTV
5 | Code Order History | ManHG
6 | Draw sequence diagram | DuyLVL, KhanhTTV
7
8
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Rating Screen
2 | Cancel order function
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week9
PROJECT REPORT
Group | Group 1
Week | 11 July 2022 to 17 July 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Modified Order Management Screen | In Progress
2 | Add pagination to all pages with lists | In Progress
3 | Code front end for product detail | In Progress
4 | Modified product detail color size tab | Completed
5 | Code Momo Integration | Completed
6 | Write SDD | In Progress
7 | Write SRS | In Progress
8 | Modified database | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Modified Order Management Screen | DuyLVL
2 | Add pagination to all pages with lists | TrungTD
3 | Code front end for product detail | NguyenPT
4 | Modified product detail color size tab | KhanhTTV
5 | Code Momo Integration | ManHG
6 | Write SDD | KhanhTTV
7 | Write SRS | ManHG
8 | Modified database | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete SRS and SDD
2 | Add register authentication
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1

## Week10
PROJECT REPORT
Group | Group 1
Week | 18 July 2022 to 23 July 2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Refine website's front-end | In Progress
2 | Add register authentication | Completed
3 | Insert meaningful data into db | In Progress
4 | Merge branches | In Progress
5 | Complete documents | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Refine website's front-end | NguyenPT
2 | Add register authentication | TrungTD
3 | Insert meaningful data into db | All members
4 | Merge branches | All members
5 | Complete documents | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1
2
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1
2
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1